## 00- Overview
Training Title/Workshop Name
Training / Site: |  |  |  | Key links:
Training dates: |  |  |  | Shared folder:
Project Manage/ Coordinator: |  |  |  | Meeting Note/Agenda:
Wet Lab Lead: |  |  |  | Playbook:
Dry Lab/ Analyst Lead :
Milestone | Timeframe | Target Date | Owner | Status | Link | Notes
Partners, roles, scope, and budget confirmed | ~6 months |  | Program Director | Start Thinking About
Communication channels, project folder, and compliance docs in place | ~6 months |  | Project Manager/Coordinator | In Progress
Host lab assessment complete; gaps and mitigation plan documented | ~5 months |  | Wet Lab Lead | Must Do Now
Procurement timeline established and planning schedule adjusted | ~5 months |  | Wet Lab Lead | Completed
Training project and sample source locked | ~4 months |  | Program Director | Start Thinking About
Reagents and equipment list reviewed; orders placed | ~4 months |  | Wet Lab Lead | Start Thinking About
All reagents ordered. Target receipt at least 2 months before workshop. | ~4 months |  | Project Manager/Coordinator | Start Thinking About
Recruitment launched and applications open | ~4 months |  | Program Director | Start Thinking About
Trainee roster finalized and notified | ~3 months |  | Wet Lab Lead; Analysis Lead | Start Thinking About
Invitation letters issued (if applicable) | ~3 months |  | Project Manager/Coordinator | Start Thinking About
Samples extracted, aliquoted, and metadata prepared | ~3 months |  | Wet Lab Lead | Start Thinking About
Reagents and samples received, verified, and confirmed in-lab. | ~2 months |  | Project Manager/Coordinator | Start Thinking About
Workshop schedule, protocols, and trainer assignments confirmed | ~2 months |  | Wet Lab Lead; Analysis Lead | Start Thinking About
Dry run completed and workflow confirmed | ~1 month |  | Wet Lab Lead | Start Thinking About
All materials finalized, uploaded, and compute access validated | ~1 month |  | Wet Lab Lead; Analysis Lead | Start Thinking About
Final logistics confirmed (travel, facility, catering, emergency plan) | ~1 month |  | Project Manager/Coordinator | Start Thinking About
Training delivered | Workshop day |  | Wet Lab Lead; Analysis Lead | Start Thinking About
Survey + report complete | Post-training |  | Project Manager/Coordinator | Start Thinking About

## 01-Pre-Training
Timeframe | Meeting # | Task All tasks are the responsibility of the host institution, either to execute directly or to ensure completion. | Owner Roles | Supporting Roles | Due Date | Status | Priority | Deliverables | Link/ Folder | Notes
Partnership & Roles
~6 months | 1 | Identify and confirm collaborating partners/ institution | Program Director | Project Manager/Coordinator |  | Not started | High | Confirmed partner list
~6 months | 1 | Identify trainers and support staff | Program Director | Wet Lab Lead; Analysis Lead |  | In progress | Med | Confirmed trainer list
~6 months | 1 | Clarify roles, expectations, and levels of engagement | Program Director | All Team Leads |  | Blocked | Low | Roles & responsibilities doc
~6 months | 1 | Ensure collaboration agreements are drafted and executed | Program Director | Project Manager/Coordinator |  | Completed | Med | Signed agreements
Scope & Planning
~6 months | 1 | Identify target trainee profile and anticipated cohort size | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Trainee profile doc
~6 months | 1 | Align on scope, objectives, and tentative training dates | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Scope summary
~6 months | 1 | Define high-level training goals and intended outcomes | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Training goals doc
~6 months | 1 | Establish funding expectations and responsibilities — clarify who pays for what (travel, per diem, reagents, shipping, printing, venue) | Program Director | Project Manager/Coordinator |  |  |  | Budget framework
~6 months | 1 | Clarify catering, meals, and per diem responsibilities — confirm who is covering costs | Program Director | Project Manager/Coordinator |  |  |  | Catering/per diem plan
~6 months | 1 | Ensure a working budget is drafted and approved | Program Director | Project Manager/Coordinator |  |  |  | Approved budget
Communication & Coordination
~6 months | 2 | Set up communication channels (Slack, email, recurring meetings) | Project Manager/Coordinator | All team members |  |  |  | Slack workspace; email list
~6 months | 2 | Establish a recurring planning cadence (e.g., biweekly check-ins) | Project Manager/Coordinator | All team members |  |  |  | Meeting schedule
~6 months | 2 | Share project folder (e.g, via Google Drive) | Project Manager/Coordinator | All team members |  |  |  | Shared folder link
~6 months | 2 | Maintain preparation checklist / action tracker | Project Manager/Coordinator | All Team Leads |  |  |  | Updated tracker
~6 months | 2 | Store regulatory documents and agreements for institutional records | Project Manager/Coordinator | All Team Leads |  |  |  | Document archive
Team Formation
~5 months | 3 | Confirm trainers and support staff | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Confirmed team roster
~5 months | 3 | Confirm host lab point of contact for facilities and local logistics | Program Director | Project Manager/Coordinator |  |  |  | Host POC confirmed
Venue & Infrastructure
~5 months | 3 | Conduct preliminary (virtual) host laboratory assessment to evaluate space, equipment, personnel, and workflow capacity. | Wet Lab Lead Scientist | Project Manager/Coordinator; Analysis Lead |  |  |  | Lab readiness report
~5 months | 3 | Confirm IT and computing readiness (internet connectivity) | Analysis Lead Scientists | Project Manager/Coordinator |  |  |  | IT readiness confirmed
~5 months | 3 | Confirm trainee capacity based on sapce and worksflow contraints | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Max trainee count confirmed
~5 months | 3 | Identify backup or contigency plan for critical equipment | Wet Lab Lead Scientist | Program Director |  |  |  | Contingency plan documented
Procurement readiness
~5 months | 3 | Assess local procurement conditions — shipping routes, customs timelines, local suppliers, and known delays | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Procurement conditions assessed
~5 months | 3 | Estimate a realistic procurement timeline based on local conditions. Target: all reagents received at least 2 months before the workshop | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Procurement timeline confirmed
~5 months | 3 | Adjust overall planning schedule based on procurement timeline estimate | Project Manager/Coordinator | Wet Lab Lead; Program Director |  |  |  | Adjusted planning schedule
Training Project & Sample Planning
~4.5 months | 4 | Finalize training goals based on site assessment findings | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Finalized goals doc
~4.5 months | 4 | Decide on training project and workflow focus | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Training project decision
~4.5 months | 4 | DECISION: Sample source selection - biobank (already approved) vs. synthetic samples. Recommendation: Synthetic samples are strongly preferred. Use biobank only if well-stored, previously approved, and suitable. | Wet Lab Lead Scientist | Project Manager/Coordinator; Program Director |  |  |  | Sample source decision
~4.5 months | 4 | Identify training sample sets and preparation approach based on decision above | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Sample plan
~3 months | 7 | Ensure samples are extracted and aliquots ahead of time if needed | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Aliquots prepared
~3 months | 7 | Prepare sample metadata | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Sample metadata sheet
Reagents, Consumables & Equipment
~4.5 months | 4 | Review equipment and reagents /consumables list against confirmed workflow | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Reviewed reagent/equipment list
~4 months | 5 | Order reagents/ consumables; confirm delivery timelines — adjust if local procurement conditions require earlier ordering | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Purchase orders placed
~4 months | 5 | Confirm recommended equipment list; reserve or procure anything missing | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Equipment checklist complete
~4 months | 5 | Maintain inventory tracking and storage plan | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Inventory log
~4 months | 5 | Ensure at least one extra sequencing kit is available if feasible | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Backup kit confirmed
~4 months | 5 | MILESTONE: All reagents ordered by this point. Target receipt at least 2 months before workshop to account for supply chain delays, customs clearance, and potential re-ordering. | Project Manager/Coordinator | Wet Lab Lead |  |  |  | All reagents ordered
Shipment (if applicable)
~3 months | 7 | Decide what will be shipped vs. sourced locally | Wet Lab Lead Scientist | Project Manager/Coordinator |  |  |  | Shipment vs. local sourcing decision
~3 months | 7 | Confirm sender and receiver points of contact | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Contact list confirmed
~3 months | 7 | Confirm temperature requirements and packaging method | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Packaging plan confirmed
~3 months | 7 | Confirm shipment documentation and permits (import/export permits, who is responsible for obtaining them) | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Shipment docs confirmed
~3 months | 7 | Confirm required approvals and documentation (MTAs, courier restrictions) | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Approvals confirmed
~2.5 months | 7 | Coordinate and execute courier shipment | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Shipment executed
~2 months | 7 | Reagent Receipt, verification and confirmation | Project Manager/Coordinator | Wet Lab Lead |  |  |  | Receipt confirmation
Recruitment Launch & Trainee Selection
~4 months | 5 | Define trainee selection process and eligibility criteria | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Selection criteria doc
~4 months | 5 | Develop recruitment materials and outreach plan | Wet Lab Lead; Analysis Lead Scientists | Project Manager/Coordinator |  |  |  | Recruitment materials
~4 months | 5 | Launch trainee recruitment and open applications | Wet Lab Lead; Analysis Lead Scientists | Program Director; Project Manager/Coordinator |  |  |  | Application open
~3 months | 6 | Review applications and select trainees; maintain a waiting list | Wet Lab Lead; Analysis Lead Scientists | Program Director |  |  |  | Trainee selection list
~3 months | 6 | Notify selected trainees and waitlist | Project Manager/Coordinator | Program Director |  |  |  | Notification emails sent
~3 months | 6 | DECISION: Are international participants attending? If yes, host provides invitation letter — participants are responsible for their own visa applications | Project Manager/Coordinator | Program Director |  |  |  | Invitation letters issued if applicable
~3 months | 6 | Collect trainee information forms | Project Manager/Coordinator | -- |  |  |  | Trainee info forms collected
~3 months | 6 | Share Visitor Guide; send expectations and prep materials (if applicable) | Project Manager/Coordinator | Wet Lab Lead; Analysis Lead |  |  |  | Prep materials sent
Curriculum & Training Materials
~2 months | 8 | Create workshop schedule and daily flow | Wet Lab Lead; Analysis Lead Scientists | Project Manager/Coordinator |  |  |  | Workshop schedule
~2 months | 8 | Assign trainers to sessions | Program Director | Wet Lab Lead; Analysis Lead |  |  |  | Trainer assignments confirmed
~2 months | 8 | Prepared laboratory protocols | Wet Lab Lead; Analysis Lead Scientists | Analysis Lead; Program Director |  |  |  | Lab protocol docs
~1.5 months | 8 | Conduct a dry run or protocol test to confirm worlflow before workshop | Wet Lab Lead; Analysis Lead Scientists | Analysis Lead |  |  |  | Dry run completed
~2 months | 8 | Develop workshop handouts, slide decks, booklet | Wet Lab Lead; Analysis Lead Scientists | Project Manager/Coordinator |  |  |  | Training materials
~2 months | 8 | Compile Seqto ID/ computational training materials (datasets, exercises, account needed). | Analysis Lead Scientists | Project Manager/Coordinator |  |  |  | Computational materials
~1.5 months | 8 | Upload materials to a shared “ Training Material” folder | Wet Lab Lead; Analysis Lead Scientists | Project Manager/Coordinator |  |  |  | Shared folder updated
~1 month | 8 | Print workshop booklets/handouts (if printing is planned) | Project Manager/Coordinator | Wet Lab Lead; Analysis Lead |  |  |  | Printed materials
Final Preparation
~1 month | 9 | Initiate the communication plan | Project Manager/Coordinator | Wet Lab Lead; Analysis Lead; Project Manager/Coordinator |  |  |  | Comms plan activated
~1 month | 9 | Confirm travel and accommodation logistics for trainees if not local | Project Manager/Coordinator | Program Director |  |  |  | Travel confirmed
~1 month | 9 | Confirm trainee reimbursement process is in place if applicable | Project Manager/Coordinator | Program Director |  |  |  | Reimbursement process confirmed
~1 month | 9 | Confirm facility reservations with final trainee numbers | Project Manager/Coordinator | Wet Lab Lead; Analysis Lead |  |  |  | Facility confirmation
~1 month | 9 | Confirm catering, meals, or per diem arrangements if applicable | Project Manager/Coordinator | Program Director |  |  |  | Catering confirmed
~1 month | 9 | Share final agenda and schedule with all trainees and partners | Project Manager/Coordinator | Wet Lab Lead; Analysis Lead |  |  |  | Final agenda sent
~1 month | 9 | Confirm emergency contacts and on-site safety briefing plan | Project Manager/Coordinator | Wet Lab Lead; Program Director |  |  |  | Emergency plan confirmed
~2 weeks | 10 | Set up laboratory spaces and organize consumables and supplies | Wet Lab Lead Scientist | Analysis Lead; Project Manager/Coordinator |  |  |  | Lab setup complete
~2 weeks | 10 | Test all protocols and confirm lab is ready for Day 1 | Wet Lab Lead Scientist | Analysis Lead |  |  |  | Protocol test complete
~2 weeks | 10 | Ensure all printed and digital materials are finalized and distributed | Project Manager/Coordinator | All team members |  |  |  | Materials checklist complete

## 02- Training Delivery
Timing | Task | Owner Roles | Status | Priority | Deliverables | Notes
Week 1 | Pre-Training Lab Setup
Before Day 1 | Lab setup and protocol dry-run completed before trainees arrive | Wet Lab Lead | In progress | High | Dry run completed
Before Day 1 | Daily schedule confirmed and shared with all trainers and trainees before Day 1 | Project Manager/Coordinator | Blocked | Med | Schedule distributed
Before Day 1 | Roles assigned for each session: who leads, who floats, who handles issues | Wet Lab Lead | Completed | Low | Role assignments confirmed
Before Day 1 | Backup reagents and contingency plan confirmed for sequencing run failure | Wet Lab Lead |  |  | Contingency plan documented
Before Day 1 | Bench space organized: reagents stored, pipettes calibrated, waste containers in place, PPE available | Wet Lab Lead |  |  | Lab setup complete
Before Day 1 | All reagents in stock, within expiration date, and at correct storage temperature | Wet Lab Lead |  |  | Reagent check complete
Before Day 1 | All instruments tested: Qubit, Bioanalyzer/TapeStation, thermocyclers, centrifuges, sequencer | Wet Lab Lead |  |  | Instrument test log
Before Day 1 | Training samples extracted, aliquoted, and labeled; sample metadata complete | Wet Lab Lead |  |  | Samples ready
Before Day 1 | Trainee workbooks/handouts printed and distributed; bench assignments made | Project Manager/Coordinator |  |  | Materials distributed
Before Day 1 | Trainer communication channel set up; trainer briefing completed | Project Manager/Coordinator |  |  | Briefing completed
Before Day 1 | Set up slides, projectors, and internet connection for presentations | Project Manager/Coordinator |  |  | AV setup confirmed
Week 1 | Daily
Each morning | Trainer check-in completed before trainees arrive (5-10 minutes) | Wet Lab Lead
Each morning | Session lead confirmed for each activity today | Wet Lab Lead
Each morning | Reagents and consumables for today staged at benches | Wet Lab Lead
Each morning | Quick check-in with participants each morning | Project Manager/Coordinator
Ongoing | Attendance list kept for each session | Project Manager/Coordinator |  |  | Attendance log | Feeds post-training report appendix
Ongoing | Break times communicated clearly to participants; water/refreshments available | Project Manager/Coordinator
Ongoing | Catering set up (if applicable) | Project Manager/Coordinator
Ongoing | Pacing adjusted based on participant understanding and engagement | Wet Lab Lead
End of day | Issues from previous day reviewed and addressed; challenges documented | Wet Lab Lead
End of day | Next-day agenda and expectations provided to trainees | Project Manager/Coordinator
Week 1 | QC Checkpoints
Day 2 | Extracted nucleic acid concentrations meet minimum thresholds (Qubit) | Wet Lab Lead |  |  | QC data recorded
Day 4 | Library concentrations and size distributions meet QC criteria (Qubit + Bioanalyzer/TapeStation) | Wet Lab Lead |  |  | QC data recorded
Day 5 | Pooling and normalization calculations reviewed before loading | Wet Lab Lead
Day 5 | Sequencing run metrics confirmed within expected range after launch | Wet Lab Lead
Week 1 | End of Week
End of Week 1 | Sequencing run launched and confirmed running, OR backup dataset confirmed ready for Week 2 | Wet Lab Lead
End of Week 1 | All wet lab QC data documented and saved to shared project folder | Wet Lab Lead |  |  | QC data archived
End of Week 1 | Week 1 deviations and issues documented; key lessons summarized | Wet Lab Lead |  |  | Deviation log
End of Week 1 | Trainer debrief completed and notes saved | Wet Lab Lead |  |  | Debrief notes
End of Week 1 | Dry lab trainer briefed and confirmed ready for Week 2 | Wet Lab Lead
End of Week 1 | Trainees briefed on Week 2 schedule and expectations | Project Manager/Coordinator
Week 2 | Pre-Training Setup
Before Day 6 | Sequencing data from Week 1 uploaded to SeqtoID, OR backup dataset confirmed loaded and accessible | Analysis Lead |  |  | Data available in SeqtoID
Before Day 6 | All trainee SeqtoID accounts active and verified (trainees have logged in at least once) | Analysis Lead |  |  | Accounts verified
Before Day 6 | Backup SeqtoID account available for contingencies | Analysis Lead
Before Day 6 | All trainee devices confirmed with internet access and SeqtoID access; loaner computers available if needed | Analysis Lead
Before Day 6 | Session slide decks reviewed and adapted to training sample set | Analysis Lead
Before Day 6 | Case study datasets selected and pre-loaded in SeqtoID (if applicable) | Analysis Lead
Before Day 6 | Offline backups (screenshots or exports) downloaded in case of connectivity issues | Analysis Lead
Before Day 6 | SeqtoID worksheets and exercises printed or shared digitally | Analysis Lead
Before Day 6 | Post-training survey prepared and ready to distribute on Day 10 | Project Manager/Coordinator |  |  | Survey ready
Before Day 6 | Session schedule confirmed and shared with trainees and co-trainers | Project Manager/Coordinator
Week 2 | Daily
Each morning | Trainer check-in completed before trainees arrive | Analysis Lead
Each morning | SeqtoID access confirmed for all trainees | Analysis Lead
Each morning | Session materials distributed or accessible | Analysis Lead
End of day | Outstanding issues from previous day reviewed and addressed | Analysis Lead
Week 2 | End of Week
End of Week 2 | Trainee presentations completed (if applicable) | Analysis Lead
End of Week 2 | Post-training survey distributed and collected | Project Manager/Coordinator |  |  | Survey responses
End of Week 2 | Analysis outputs and results saved and documented | Analysis Lead
End of Week 2 | Week 2 deviations and issues documented | Analysis Lead
End of Week 2 | Trainer debrief completed and notes saved to shared project folder | Analysis Lead |  |  | Debrief notes

## 03 - Post Training
Timing | Task | Owner Roles | Status | Priority | Deliverables | Notes
Within 1 week | Post-training follow-up email sent to all trainees | Project Manager/Coordinator | Not started | High | Follow-up email sent
Within 1 week | Post-training assessment distributed and collected | Project Manager/Coordinator | In progress | Med | Assessment results
Within 2 weeks | First check-in call scheduled with trainees (if applicable) | Wet Lab Lead; Analysis Lead Scientists | Blocked | Low
Within 2 weeks | Slack channel (or equivalent) active with trainees added (if applicable) | Project Manager/Coordinator
Ongoing (~1-6 months) | Regular check-ins scheduled and conducted (if applicable) | Wet Lab Lead; Analysis Lead Scientists
Ongoing (~1-6 months) | Appendices maintained: attendance, equipment log, reagent usage | Wet Lab Lead Scientist |  |  | Appendix records
Evaluation - Trainee Feedback
Within 2 weeks | Debrief notes saved to shared project folder | Wet Lab Lead Scientist
Within 4-6 weeks | Post-training report drafted and circulated for review | Project Manager/Coordinator |  |  | Draft report
Within 4-6 weeks | Post-training report finalized and shared with stakeholders | Program Director |  |  | Final report
Evaluation - Continuous Improvement
6 months post-training | Follow-up survey sent at 6 months post-training | Project Manager/Coordinator |  |  | Follow-up survey results
Ongoing | Playbook updated based on lessons learned | Project Manager/Coordinator |  |  | Updated playbook
Ongoing | Implementation milestone data reviewed and documented | Project Manager/Coordinator

## 04- Risks
Milestone | Impact | Likelihood | Owner | Status | Notes
Regulatory approvals delayed |  |  | Project Manager/Coordinator | Not started
Reagents/equipment arrive late |  |  | Wet Lab Lead Scientist | In progress
Host lab infrastructure gaps (space/power/instrument access) |  |  | Wet Lab Lead Scientist | Blocked
Shipping/import issues (permits/courier/temp excursion) |  |  | Project Manager/Coordinator | Completed
Trainee attendance/visa issues |  |  | Project Manager/Coordinator | Not started
Compute/data access not ready for SeqtoID exercises |  |  | Analysis Lead Scientists | Not started
Critical orders placed |  |  | Wet Lab Lead; Analysis Lead Scientists | Not started
Samples + metadata ready |  |  | Wet Lab Lead; Analysis Lead Scientists | Not started
Shipping received/verified (if applicable) |  |  | Project Manager/Coordinator | Not started
Agenda + materials finalized |  |  | Project Manager/Coordinator | Not started
Compute access validated |  |  | Analysis Lead Scientists | Not started
Lab dry run completed |  |  | Wet Lab Lead; Analysis Lead Scientists | Not started
Training delivered |  |  | Wet Lab Lead; Analysis Lead Scientists | Not started

## Glossary
Term | Definition
Analysis Lead | Scientist responsible for computational and bioinformatics components of the training.
Biobank Samples | Biological samples stored in an institutional repository. May be used for workshops only if they are well-stored, previously approved for this use, and suitable for the planned workflow.
Cohort Size | The anticipated number of trainees for the workshop, determined by available lab space, equipment capacity, and workflow constraints.
Cold Chain / Temperature Requirements | The packaging and shipping conditions required to maintain sample or reagent integrity during transport, including temperature range, dry ice, and insulated packaging specifications.
Collaboration Agreement | A formal document outlining the roles, responsibilities, and expectations of each partner involved in the workshop.
Collaborating Institution / Partner | Any external organization involved in the workshop.
Communication Plan | A structured plan defining how information will be shared with trainees, partners, and team members before, during, and after the workshop, including channels, frequency, and responsibilities.
Contingency Plan | A documented backup plan identifying alternative equipment or resources to be used if critical instruments are unavailable or fail during the workshop.
Courier Coordination | The process of arranging, scheduling, and executing the shipment of samples or reagents through a third-party courier service, including documentation and tracking.
Dry Run | A full or partial rehearsal of the workshop workflow conducted before the training event to identify gaps, test protocols, and confirm that all materials and equipment are functioning correctly.
Equipment Host | Institution providing access to key instruments (e.g., sequencer, Qubit, Bioanalyzer/TapeStation) and ensuring service and maintenance readiness ahead of the workshop.
Financial Host / Funder | Entity covering workshop budget items such as travel, per diem, meals, reagents, shipping, printing, and venue costs. Clarify who pays for what early in planning.
Host Laboratory Assessment | A preliminary evaluation (typically conducted virtually via walkthrough or photos) of the host lab's space, equipment, personnel capacity, and workflow readiness. Gaps and mitigation plans should be documented.
Import/Export Permit | Official authorization required to transport biological samples or reagents across international borders.
Inventory Tracking | An ongoing log of reagents, consumables, and equipment received, stored, and used during workshop preparation, including storage conditions and quantities.
Invitation Letter | A formal letter issued by the host institution to support an international participant's visa application. The host's responsibility ends at providing this letter; participants are responsible for their own visa applications.
IRB / Ethics Approval | Institutional Review Board approval required for research involving human subjects. Note: New IRB approval is NOT typically required for workshops using previously approved samples.
IT / Computing Readiness | Confirmation that the host site has adequate internet connectivity, computers, installed software, and active accounts (e.g., CZ ID) needed for the computational components of the training.
Laboratory Protocol | A step-by-step document describing the procedures and workflows to be followed during lab sessions of the workshop.
Logistics Host | Group responsible for local logistics including procurement support, customs brokering, transport, and participant coordination. May be the physical host or a separate partner.
Milestone | A key checkpoint indicating a critical stage of preparation has been completed. Flagged with YES in the Milestone column.
MTA (Material Transfer Agreement) | A legal agreement governing the transfer of biological or chemical materials between institutions.
Physical Host / Location Host | Institution providing the venue and lab space where the workshop is delivered, including benches, biosafety infrastructure, utilities, and access.
Procurement Timeline | A realistic schedule for ordering and receiving reagents and consumables, accounting for local supply chain conditions, customs clearance, shipping delays, and potential re-ordering. Target: all reagents in-lab at least 2 months before the workshop.
Program Director | Senior lead responsible for strategic decisions, partner relationships, and overall program direction.
Project Manager / Coordinator | Responsible for operational execution, logistics, scheduling, documentation, and communications.
Sample Metadata | Descriptive information associated with training samples, including sample ID, type, storage conditions, preparation method, and any relevant clinical or experimental context.
Scope | The defined boundaries of the workshop, including objectives, training dates, format, and intended outcomes.
Support Staff | Team members providing operational, technical, or administrative support during the workshop but not delivering primary instruction.
Synthetic Samples | Commercially produced or lab-generated samples used in place of human clinical samples. Strongly recommended for workshops due to lower regulatory burden, cost, and logistical complexity.
Trainee | Workshop participant receiving instruction. Responsible for their own visa applications if traveling internationally.
Trainee Information Form | A form collected from selected trainees to gather personal details, dietary requirements, travel information, and other logistics needed for workshop planning.
Trainee Profile | A description of the target participant for the workshop, including required background, skills, institutional affiliation, and career stage.
Trainer | Subject matter expert responsible for delivering instruction during the workshop.
Training Host | Group responsible for delivering instruction, including RR trainers, guest trainers, and local trainers.
Visitor Guide | A document shared with trainees prior to the workshop outlining practical information such as travel logistics, what to bring, pre-reading, and software to install.
Waitlist | A ranked list of qualified applicants who were not selected for the primary trainee cohort but may be offered a spot if a selected trainee withdraws.
Wet Lab Lead | Senior scientist overseeing laboratory protocols, sample preparation, reagents, and equipment.
Workshop Schedule / Daily Flow | A structured agenda outlining the sequence of activities, sessions, and breaks for each day of the workshop.

## Role Definition
Tracker Role | Institution Role | Institution | Name | Title | Email | Phone / WhatsApp | Time Zone | Primary Responsibilities | Notes
Program Director | Physical Host / Location Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Senior lead responsible for strategic decisions, partner relationships, and overall program direction
Project Manager/Coordinator | Logistics Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Responsible for operational execution, logistics, scheduling, documentation, and communications
Wet Lab Lead | Training Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Senior scientist overseeing laboratory protocols, sample preparation, reagents, and equipment
Analysis Lead | Training Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Scientist responsible for computational and bioinformatics components of the training
Trainer | Training Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Subject matter expert responsible for delivering assigned sessions during the workshop
Trainer | Training Partner | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Subject matter expert responsible for delivering assigned sessions during the workshop
Trainer | Training Partner | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Subject matter expert responsible for delivering assigned sessions during the workshop
Support Staff | Logistics Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Provides operational, technical, or administrative support during the workshop
Host Lab Point of Contact | Physical Host / Location Host | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | On-site coordinator for facilities, equipment access, and local logistics
Trainee | -- | [Institution Name] | [Name] | [Title] | [Email] | [Phone/WhatsApp] | [Time Zone] | Workshop participant. Responsible for own visa application if traveling internationally.
|  | Trainer (Guest/Local/RR) | As-needed | Conditional | Delivers instruction during the workshop; may be RR, host, or guest.
|  | Support Staff (Operations/Tech/Admin) | As-needed | Conditional | Provides operational/technical/admin support during delivery (not primary instruction).