## Pre-course
[Pre-course date] | PRE-COURSE DAY 1: Site & Equipment Readiness | Start time | Topic | Details | Location (room) | Who
|  | 8.30 AM – 9.00 AM | Facilitator arrival / team check-in | Confirm access, keys, local contacts, and day priorities | [Site] | [Lead]
|  | 9.00 AM – 10.00 AM | Tour laboratory and training spaces | Verify room flow, benches, pre/post-PCR workflow, power, water, and participant movement | Lab / lecture space | [Lead + Host]
|  | 10.00 AM – 11.00 AM | Critical equipment / system checks | Confirm sequencer, thermocycler, centrifuges, Qubit/TapeStation or equivalent, and any off-site instrument access | Lab | [Technical lead]
|  | 11.00 AM – 12.00 PM | Test training infrastructure | Confirm projector/display, internet, laptops, software/accounts, shared folders, and backup access | Lecture space | [PM + Dry-lab lead]
|  | 12.00 PM – 1.00 PM | Lunch |  | [TBD]
|  | 1.00 PM – 4.00 PM | Lab setup / protocol dry run / sample preparation | Set up stations; verify reagents, consumables, sample set, controls, storage, and timing. Use buffer time for troubleshooting. | Lab | [Wet-lab team]
[Pre-course date] | PRE-COURSE DAY 2: Materials, Samples & Final Checks | Start time | Topic | Details |  | Who
|  |  | Facilitator arrival / team check-in | Review outstanding issues and assignments |  | [Lead]
|  |  | Inventory and storage review | Confirm reagents/supplies received, storage temperatures, locations, and contingency supplies |  | [PM + Wet-lab lead]
|  |  | Participant materials and registration setup | Prepare registration list, booklets/handouts, forms, name materials, signage, and participant communications |  | [PM / Host]
|  |  | Final training material and data-access check | Confirm final slides, protocols, activities, datasets, SeqtoID/analysis accounts, and shared-drive permissions |  | [Lead trainers]
Lunch
|  |  | Final readiness / go-no-go review | Walk through Day 1; confirm trainer roles, transportation, catering, AV, Wi-Fi, samples, reagents, equipment, and backup plans |  | All facilitators
[Optional buffer date] | OPTIONAL PRE-COURSE / BUFFER DAY | Start time | Topic | Details | Location (room) | Who
|  | 8.30 AM – 9.00 AM | Team check-in | Use only if an additional preparation/buffer day is needed | [Site] | [Lead]
|  | 9.00 AM – 10.00 AM | [Insert preparation task]
|  | 10.00 AM – 11.00 AM | [Insert preparation task]
|  | 11.00 AM – 12.00 PM | [Insert preparation task]
|  | 12.00 PM – 1.00 PM | Lunch
|  | 1.00 PM – 4.00 PM | Buffer / final troubleshooting

## Week 1 WET LAB
WEEK 1 - WET LAB
[Monday / Date] | DAY 1: Welcome, Training Overview & mNGS Foundations | Start time | Topic | Details | Slide deck number | Protocol number | Activity number | Location (room) | Who | Notes
|  | 8.00 AM – 8.30 AM | Arrival and registration |  |  |  |  | Lecture space
|  | 8.30 AM – 9.30 AM | Welcome and introductions | Introduce host/facilitators; participant introductions; review workshop expectations | [Slide ID] |  | [Icebreaker / intro activity] | Lecture space | [Lead / Host]
|  | 9.30 AM – 10.30 AM | Training overview & learning objectives | Review training goals, schedule, outputs, and participant expectations | [Slide ID] |  |  | Lecture space | [Lead trainer]
|  | 10.30 AM – 10.45 AM | Break
|  | 10.45 AM – 12.00 PM | mNGS foundations / study design / use cases | Adapt content to workshop goals and trainee baseline | [Slide ID] |  |  | Lecture space | [Instructor]
|  | 12.00 PM – 1.00 PM | Lunch |  |  |  |  | Lecture space
|  | 1.00 PM – 1.45 PM | Sample workflow / sample-set overview | Introduce training samples, controls, QC expectations, and workflow | [Slide ID] |  |  | Lecture space | [Instructor]
|  | 1.45 PM – 3.30 PM | Core lab technique / practice | Examples: pipetting, SPRI clean-up, Qubit, sample QC, or other foundational practice |  | [Protocol ID] | [Activity ID] | Lab | [Wet-lab team]
|  | 3.30 PM – 4.00 PM | Daily recap / feedback / departure | Confirm next-day expectations and any facilitator follow-up
[Tuesday / Date] | DAY 2: Wet Lab I — Sample QC & Library Preparation | Start time | Topic | Details | Slide deck number | Protocol number | Activity number | Location (room) | Who | Notes
|  | 8.00 AM – 8.30 AM | Arrival and registration
|  | 8.30 AM – 10.45 AM | Wet-lab workflow overview & theory | Review sample types, extraction/QC approach, library preparation workflow, QC, and sequencing; include break as needed | [Slide ID] |  |  | Lecture space | [Instructor]
|  | 10.45 AM – 11.00 AM | Case / sample set review | Confirm samples and group assignments | [Slide ID] |  |  | Lecture space | [Instructor]
|  | 11.00 AM – 12.00 PM | Lunch
|  | 12.00 PM – 5.00 PM | Library preparation — Part I | Workflow-specific hands-on block; build in a short break and troubleshooting buffer |  | [Protocol ID] |  | Lab | [Wet-lab team] | Adjust end time to local needs
[Wednesday / Date] | DAY 3: Wet Lab II — Library Preparation & QC | Start time | Topic | Details | Slide deck number | Protocol number | Activity number | Location (room) | Who | Notes
|  | 8.00 AM – 8.30 AM | Arrival and registration
|  | Before session | Facilitator lab prep | Thaw/prep reagents, confirm instruments and stations, review any overnight issues |  |  |  | Lab | Facilitators only | Behind-the-scenes task
|  | 8.30 AM – 12.00 PM | Library preparation — Part II | Continue workflow; include QC and cleanup steps appropriate to protocol |  | [Protocol ID] |  | Lab | [Wet-lab team]
|  | 12.00 PM – 1.00 PM | Lunch
|  | 1.00 PM – 2.30 PM | Library QC / sequencing theory | Introduce QC methods, acceptance criteria, sequencing concepts, and troubleshooting | [Slide ID] |  |  | Lecture space | [Instructor]
|  | 2.30 PM – 2.45 PM | Break
|  | 2.45 PM – 4.00 PM | Library QC / troubleshooting | Perform required QC and decide next steps |  | [Protocol ID] | [Activity ID] | Lab | [Wet-lab team]
|  | After / behind the scenes | Facilitator QC / setup | Run any facilitator-only QC, calculations, or setup needed for the next day |  | [Protocol ID] |  | Lab | Facilitators only
[Thursday / Date] | DAY 4: Wet Lab III — Pooling / Sequencing Preparation | Start time | Topic | Details | Slide deck number | Protocol number | Activity number | Location (room) | Who | Notes
|  | 8.00 AM – 8.30 AM | Arrival and registration
|  | 8.30 AM – 9.30 AM | QC review & troubleshooting | Review prior-day results and resolve issues before proceeding |  |  |  | Lab | [Wet-lab team]
|  | 9.30 AM – 9.45 AM | Break
|  | 9.45 AM – 11.30 AM | Pooling / sequencing-prep theory | Review pooling strategy, calculations, and platform-specific requirements | [Slide ID] |  | [Worksheet / activity] | Lecture space | [Instructor]
|  | 11.30 AM – 12.30 PM | Lunch
|  | 12.30 PM – 1.45 PM | Pooling / sequencing preparation — lab | Prepare pools and perform required QC |  | [Protocol ID] |  | Lab | [Wet-lab team]
|  | 1.00 PM – 2.30 PM | Background QC / instrument time | Use for QC assays or instrument runs occurring in parallel |  |  |  | Lab | [Assigned facilitator] | Overlap intentionally if appropriate
|  | 2.00 PM – 2.45 PM | Sequencing platform overview / guest session | Platform overview, workflow, troubleshooting, or invited technical session | [Slide ID] |  |  | Lecture space | [Instructor / guest]
|  | 2.45 PM – 3.30 PM | Results review / loading readiness | Review QC results and confirm next steps / loading readiness |  |  |  | Lab / lecture space | [Wet-lab team]
|  | 3.30 PM – 4.00 PM | Daily recap / departure
[Friday / Date] | DAY 5: Sequencing, Review & Week 1 Wrap-Up | Start time | Topic | Details | Slide deck number | Protocol number | Activity number | Location (room) | Who | Notes
|  | 8.00 AM – 8.30 AM | Arrival and registration
|  | 8.30 AM – 9.00 AM | Review | Review hands-on workflow, QC, and unresolved questions |  |  |  | Lecture space | [Lead trainer]
|  | 9.00 AM – 10.00 AM | Sequencing workflow / troubleshooting / support | Include platform-specific best practices and support escalation guidance | [Slide ID] |  |  | Lecture space | [Instructor / platform expert]
|  | 10.00 AM – 10.15 AM | Break
|  | 10.15 AM – 11.00 AM | Sequencer loading theory / calculations | Review sample sheet, denaturation/dilution, loading steps, and calculations as applicable | [Slide ID] | [Protocol ID] | [Worksheet] | Lecture space | [Instructor]
|  | 11.00 AM – 12.00 PM | QC buffer / review / optional journal club | Protected buffer for troubleshooting, catch-up, review, or optional learning activity |  |  |  | Lecture space / Lab | [Team] | Best-practice buffer carried forward from prior workshops
|  | 12.00 PM – 1.00 PM | Lunch |  |  |  |  | Lecture space
|  | 1.00 PM – 3.30 PM | Sequencer loading / run start | Complete platform-specific loading and run initiation |  | [Protocol ID] |  | Lab | [Wet-lab team]
|  | 3.30 PM | Week 1 workshop survey | Collect participant feedback before transition to Week 2 |  |  | [Survey link] |  | [PM / Lead]
|  | 3.30 PM – 4.00 PM | Week 1 wrap-up / departure | Confirm Week 2 expectations, data availability, and any participant preparation

## Week 2 DRY LAB
WEEK 2- DRY LAB
[Monday / Date] | Start time | Topic | Slide deck number | Activity number | Location (room) | Facilitator | Notes
| 8.00 AM – 8.30 AM | Arrival and registration |  |  | Lecture space / computer lab
| 8.30 AM – 9.30 AM | Introductions and syllabus overview | [Slide ID] |  |  | [Lead]
| 9.30 AM – 10.45 AM | Wet-lab recap / methods used in WGS and mNGS | [Slide ID] |  |  | [Instructor] | Adapt depth to participant baseline
| 10.45 AM – 11.00 AM | Break
| 11.00 AM – 11.30 AM | Sequencing run quality control / platform review | [Slide ID] | [Run review resource] |  | [Instructor / platform expert]
| 11.30 AM – 12.00 PM | Sequencing run review activity |  | [Activity ID / booklet pages] |  | [Facilitator]
| 12.00 PM – 1.00 PM | Lunch
| 1.00 PM – 2.30 PM | Bioinformatics basics | [Slide ID] |  |  | [Instructor]
| 2.30 PM – 2.45 PM | Break
| 2.45 PM – 3.30 PM | Foundational analysis activity / BLAST |  | [Activity ID / booklet pages] |  | [Facilitator]
| 3.30 PM – 4.00 PM | Daily recap / departure
[Tuesday / Date] | Start time | Topic | Slide deck number | Activity number | Location (room) | Facilitator | Notes
| 8.00 AM – 8.30 AM | Arrival and registration |  |  | Lecture space / computer lab
| 8.30 AM – 9.00 AM | Introduction to analysis platform | [Slide ID] |  |  | [Instructor]
| 9.00 AM – 10.00 AM | mNGS analysis pipeline overview | [Slide ID] |  |  | [Instructor]
| 10.00 AM – 10.15 AM | Break
| 10.15 AM – 11.00 AM | Sample QC and interpretation | [Slide ID] |  |  | [Instructor]
| 11.00 AM – 12.00 PM | Sample QC activity |  | [Activity ID / booklet pages] |  | [Facilitator]
| 12.00 PM – 1.00 PM | Lunch
| 1.00 PM – 2.00 PM | Sample report metrics / interpretation | [Slide ID] |  |  | [Instructor]
| 2.00 PM – 3.30 PM | Sample report activity |  | [Activity ID / booklet pages] |  | [Facilitator]
| 3.30 PM – 4.00 PM | Daily recap / departure
[Wednesday / Date] | Start time | Topic | Slide deck number | Activity number | Location (room) | Facilitator | Notes
| 8.00 AM – 8.30 AM | Arrival and registration |  |  | Lecture space / computer lab
| 8.30 AM – 9.30 AM | Contamination / background model correction | [Slide ID] |  |  | [Instructor]
| 9.30 AM – 10.30 AM | Heat map analysis | [Slide ID] |  |  | [Instructor]
| 10.30 AM – 10.45 AM | Break
| 10.45 AM – 12.00 PM | Heat map analysis activity |  | [Activity ID / booklet pages] |  | [Facilitator]
| 12.00 PM – 1.00 PM | Lunch
| 1.00 PM – 2.00 PM | Consensus genomes / sequence analysis | [Slide ID] |  |  | [Instructor] | Can substitute genomic epidemiology/phylogenetics depending on objectives
| 2.00 PM – 3.00 PM | Consensus genome / sequence-analysis activity |  | [Activity ID / booklet pages] |  | [Facilitator]
| 3.00 PM – 4.00 PM | Review / knowledge check / game | [Optional] | [Optional activity] |  | [Facilitator] | Use for review and identifying concepts needing reinforcement
[Thursday / Date] | Start time | Topic | Slide deck number | Activity number | Location (room) | Facilitator | Notes
| 8.00 AM – 8.30 AM | Arrival and registration |  |  | Lecture space / computer lab
| 9.00 AM – 11.30 AM | Mystery case introduction + group work |  | [Activity ID / booklet pages] |  | [Facilitators] | Include a short break during group work
| 11.30 AM – 12.00 PM | Guest lecture / applied case example |  |  |  | [Guest speaker] | Optional; confirm AV/Zoom in advance
| 12.00 PM – 1.00 PM | Lunch
| 1.00 PM – 2.30 PM | Continue mystery case work / presentation preparation |  | [Activity ID / booklet pages] |  | [Facilitators]
| 2.30 PM – 3.30 PM | Journal club / genomic epidemiology / applied discussion | [Slide / paper ID] | [Reading / booklet pages] |  | [Instructor] | Select based on workshop goals
| 3.30 PM – 4.00 PM | Daily recap / departure
[Friday / Date] | Start time | Topic | Slide deck number | Activity number | Location (room) | Facilitator | Notes
| 8.00 AM – 8.30 AM | Arrival and registration |  |  | Lecture space / computer lab
| 9.00 AM – 9.30 AM | Guest lecture / applied case example |  |  |  | [Guest speaker] | Optional
| 9.30 AM – 10.00 AM | Break
| 10.00 AM – 11.00 AM | Prepare final case presentations |  |  |  | [Facilitators]
| 11.00 AM – 12.00 PM | Case study presentations |  |  |  | Participant groups
| 12.00 PM – 1.00 PM | Lunch
| 1.00 PM – 1.30 PM | Week 2 workshop survey |  | [Survey link] |  | [PM / Lead]
| 1.30 PM – 1.45 PM | Resource review / post-training support |  | [Resource link] |  | [Lead trainers] | Review shared resources, support channels, and mentorship cadence
| 1.45 PM – 2.45 PM | Workshop wrap-up / certificates / next steps |  |  |  | [Host + Lead trainers] | Confirm next steps and post-training support
| 3.00 PM | Departure

## Facilitator logistics
Task | Date/time | Done? | Lead | Support | Deadline | Notes | Institution | Name | Phone / WhatsApp | Email | Role | Notes
Print registration list / protocols / participant materials | [Before Day 1] |  | [PM] | [Host] | Before workshop |  | [Institution] | [Name] | [Phone / WhatsApp] | [Email] | [Role] | [Notes]
Confirm transportation / pickups, if applicable | [Before Day 1] |  | [PM] | [Host] | Before workshop
Set up registration area | Day 1 |  | [PM] | [Host] | Before arrival | Booklets, pens, consent forms, registration list, name materials
Confirm bathrooms, drinking water, emergency contacts, and building access | Day 1 |  | [PM] | [Host] | Before arrival
Register participants / capture attendance | Daily |  | [PM] | [Host] | Daily
Collect required media / consent forms | Day 1 |  | [PM] | [Host] | Day 1 | If applicable
Share workshop Drive / resources and troubleshoot access | Day 1 |  | [Dry-lab lead] | [PM] | Day 1
Welcome / opening logistics | Day 1 |  | [Lead] | [Host] | Day 1
Morning didactic support | Daily |  | [Lead trainer] | [Facilitator] | Daily
Lab station setup / reset | Daily |  | [Wet-lab lead] | [Facilitators] | Daily
Guest speaker / virtual session connection test | As needed |  | [PM] | [Session lead] | Before session
Daily end-of-day facilitator debrief | Daily |  | [Lead] | All facilitators | Daily | Capture issues, changes, and next-day actions
Next-day materials / room readiness | Daily |  | [PM] | [Lead trainers] | Daily
Directional signage / campus access instructions | Not started | [Host] | [PM] | [PM] | Before workshop
Create participant/facilitator communication group | Not started | [Host] | [PM] | [PM] | Before workshop | WhatsApp/Slack/email as appropriate
Send introduction / instruction emails | Not started | [Host] | [PM] | [PM] | Before workshop | Include schedule, location, expectations, and prep
Wi-Fi / internet troubleshooting plan | Not started | [Host] | [PM] | [PM] | Before + daily | Do not store passwords in this workbook
Lunch and snack coordination | Not started | [Host] | [PM] | [PM] | Daily | Confirm timing and dietary needs
Photos/videos during workshop | Not started | [Host] | [PM] | [PM] | Daily | Only where consent requirements are met
Room key / projector / computer / AV setup | Not started | [Host] | [PM] | [PM] | Daily
Power outlets / extension cords / charging access | Not started | [Host] | [PM] | [PM] | Before workshop
Workshop materials / data access | [5 empty] | Notes
Create participant copy of schedule and share | Not started | [Host] | [PM] | [PM] | Before workshop
Upload training data to backup analysis project | Not started | N/A | N/A | [Dry-lab lead] | Before Week 2
Prepare icebreaker / interactive review activity | Not started | N/A | [Trainer] | [Trainer] | Before workshop | Optional
Move/share daily training materials | Not started | N/A | [Trainer] | [Trainer] | Daily | Confirm participants have correct version
Upload workshop-generated sequencing data | Not started | N/A | N/A | [Dry-lab lead] | Before analysis session
Share analysis projects/accounts with participants + troubleshoot access | Not started | N/A | N/A | [Dry-lab lead] | Before Week 2
Lab tasks | [5 empty] | Notes
Confirm daily lab point of contact, keys, reagent locations, and room access | Not started | [Host] | [Wet-lab lead] | N/A | Daily
Prepare sample-set overview materials | Not started | N/A | [Wet-lab lead] | N/A | Before session
Sample-set aliquoting / labeling / inventory | Not started | N/A | [Wet-lab lead] | N/A | Before use
Confirm QC instrument access / consumables / operator | Not started | [Host] | [Wet-lab lead] | N/A | Before use | TapeStation/Qubit/gel system or equivalent
Before travel / workshop launch | [5 empty] | Notes
Prepare Week 1 and Week 2 feedback surveys | Not started | N/A | [PM / Evaluation lead] | [PM / Evaluation lead] | Before workshop
Prepare certificates for participants and hosts/facilitators | Not started | [Host] | [PM] | [PM] | Before workshop
Print workshop booklets / handouts | Not started | [Host / PM] | [PM] | [PM] | Before workshop | Use final trainee count + extras
Prepare and pack workshop materials | Not started | N/A | [PM / Trainers] | [PM / Trainers] | Before workshop
Finalize training sample list | Not started | N/A | [Wet-lab lead] | N/A | Before workshop
Participant recognition / prizes, if applicable | Not started | [Host / PM] | [PM] | [PM] | Before workshop | Optional

## Lab Clean Up
Done? | Item / Action | Quantity | Notes | Storage / Transport | Destination / Institution | General Contents / Final Disposition
FALSE | Loaned equipment to return | [Qty] | Confirm all parts/accessories/chargers | Room temp / as required | [Home institution]
FALSE | Computers / chargers / adapters | [Qty] |  | Room temp | [Home institution]
FALSE | Unused room-temperature consumables | [Qty] | Inventory and repack | Room temp | [Return / Host / Donate]
FALSE | Unused 4°C reagents | [Qty] | Verify condition and disposition | 4°C | [Return / Host / Donate]
FALSE | Unused -20°C reagents | [Qty] | Verify condition and disposition | -20°C | [Return / Host / Donate]
FALSE | Unused -80°C reagents / controls / samples | [Qty] | Verify condition and disposition | -80°C | [Return / Host / Donate]
FALSE | Sequencing kits / flow cells | [Qty] | Document lot/remaining kits as appropriate | Per manufacturer | [Return / Host / Donate]
FALSE | Training samples / controls | [Qty] | Confirm approved disposition and metadata records | As required | [Destination]
FALSE | Workshop documents / registration / consent records | [Qty] | File per institutional requirements | N/A | [Institutional records]
FALSE | Donation to host institution — room temperature | [Qty] | Document contents and handoff | Room temp | [Host institution]
FALSE | Donation to host institution — 4°C | [Qty] | Document contents and handoff | 4°C | [Host institution]
FALSE | Donation to host institution — -20°C | [Qty] | Document contents and handoff | -20°C | [Host institution]
FALSE | Donation to host institution — -80°C | [Qty] | Document contents and handoff | -80°C | [Host institution]
FALSE | Prepare final donation/return inventory |  | Record box counts and contents |  | [Destination]
FALSE | Emergency / contingency kit disposition |  | Confirm unused contingency supplies | As required | [Destination]
FALSE | Lab consumables / station materials |  | Return, donate, or dispose as planned | Room temp | [Destination]
FALSE | Waste / disposal confirmation |  | Confirm waste streams and local disposal requirements | N/A | [Host]
FALSE | Final room / bench reset |  | Clean, decontaminate, and return space to host | N/A | [Host]
FALSE | Final inventory / photos / handoff confirmation |  | Document final disposition where useful | N/A | [PM / Host]
FALSE | Outstanding follow-up |  | List anything that remains unresolved | N/A | [Owner]

## Certification Info
Trainees | Workshop participation | Certificate of Achievement | Notes
[Trainee name] | [Week 1 / Week 2 / Both] | [Yes / No] | [Notes]